## Sheet1
Data Processor Gantt Chart		Key
		Alex
		Daryl
		Both

#	Task	Week 16 , 13th Feb 2017					Week 17, 20th Feb 2017					Week 18, 27th Feb 2017					Week 19, 6th March 2017					Week 20, 13th March 2017					Week 21, 20th March 2017
		13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26
1	Project Meeting
2	State Assignment of Data Processing
3	Handshaking implementation between data processor and generator
4	State diagrams and understanding the specification						I
5	Project Meeting						N
6	Correct retrieval of data from command processor						T
7	Module to parse and verify the Rx commands						E
8	Retrieval of all seven bytes (including middle peak)						R
9	Interface module between cmdParse and the Tx module						I
10	Project Meeting						M
11	Added a Parent module for sub entities to inherit from
12	Added sub entity to process L commands						D
13	Ported code onto GitHub with initial commit						E
14	Added sub entity to process P commands						A
15	Implemented a handshaking protocol between sub entities						D
16	Correct determination of the peak value						L
17	Correct output of data to the command processor						I
18	Integrated code into the port mapping of the parent module						N
19	Project Meeting						E
20	Enforced sub entities to interface through the parent for Tx printing
21	Interim report write up
22	Final Debugging
23	Project Meeting